## Business Plan
Cornwall Heritage Trust
DRAFT Business Plan
Year 1 - 2026-2027
Pillar: Resilient Organisation
Ambition: Strengthen Cornwall Heritage Trust’s foundations to enable delivery of the charitable objectives through the strategic plan
Action | Timescale | Lead | Additional support & involvement | Sub Committee | Budget and source of funding | Performance indicator(s) | Progress | Monitoring
1.1 Build and Diversify Revenue streams to achieve sustainable annual income of £2m, of which £1m is unrestricted, by 2031. Unrestricted funds to at least break even
Create a role description for a Business Development Manager role | Quarter 1 | CW | SLT, Finance Manger | Finance | No additional cost | Sign-off to advertise role
Advertise and recruit Business Development Manager role | Quarter 2 | CW | SLT and Finance Committee for interviews |  | Salary to be a revenue expense linked to the strategic plan | Role successfully recruited and in post
Revisit the Fundraising Strategy | Quarter 2 | CW | SLT, Fundraising Officer |  | No additional cost | Review undertaken, decision made regarding commissioning external support
Research options for income generation | Quarter 3 | Income Generation Mgr | CW, SLT, Finance Manger |  | No additional cost | Options appraisal complete
Consider solutions | Quarter 4 | Income Generation Mgr | CW, SLT, Finance Manger |  | No additional cost | Plan in place to inform the creation of strategies
Formulate an Income Generation Strategy | Quarter 4 | Income Generation Mgr & CW | SLT, Finance Manger |  | No additional cost | Creation of a draft Income Generation Strategy
Create a Business Plan for implementation | Quarter 4 | Income Generation Mgr & CW | SLT, Finance Manger |  | No additional cost | Creation of a draft Business Plan
1.2 Strengthen governance and support functions to underpin the organisation’s growth
Creation and implementation of a robust, challenging but achievable strategic plan with associated detailed Business Plan for Year 1 (2026/27) | Pre Year 1 | Trustees and SLT | Sara Hilton | Council of Mgt | Costs for trustee workshop only - revenue budget, paid in 25/26 revenue budget | Strategic Plan agreed and in place, supported by a Business Plan for Year 1
Carry out skills audit for trustees alongside creating a succession plan | Year 1 | Trustees and CW |  |  | Initial skills audit exercise will be cost neutral | Skills audit, including succession planning, completed and outcomes presented to trustees
Ensure policies and procedures are in place for a growing organisation | Year 1 | Trustees and SLT |  |  | No additional cost | All policies reviewed and updated where required. HRE Express policy review undertaken by Stephens Scown
Review sub committee terms of reference | Year 2
1.3 Review people team in line with expanding activity to enable delivery of the ambitions of the charity
Identify the level of investment required to future-proof the sites team with the resources needed to manage the sites well | Year 1 | CW | Sites Officer, Project Manager, Finance Manager | Property and Finance | No additional cost | Production of a costed resource plan for sites management
Recruit as required to fulfil the requirements of the Strategic Plan | Year 1 | CW | Finance Committee (for interviews) and SLT | Finance | Cost of recruitment advertising | Successful recruitment of a BDM and Sites Manager
Identify new solutions for technology etc | Year 2
Explore options for a permanent headquarters for CHT | Year 2
Seek funding to help with the cost | Year 1 & 2 | CW | Finance Manager, BDM and Fundraising Officer | Finance | No additional cost | Ongoing - applications submitted
1.4 Creation of a resource plan to ensure that the teams are fully equipped to meet the needs of increased activity.
Create a resources strategy for the rolling replacement and renewal of essential kit throughout the organisation e.g. laptops | Year 1 | Finance Manager and CW | Operations Manager | Finance | No additional cost | Production of a costed resources strategy for the office/ staff
Capital Works Plan to be formulated for all sites | Year 1 | Sites Officer, Proj Mgr, Rangers | CEO and Finance Manager | Property | No additional cost | Production of a full Capital Works Plan for all sites
1.5 Patron - Seek high-profile patrons to help spread the word about Cornwall’s heritage and the charity
Identify potential Patrons | Years 2 & 3
Plan approaches
Pillar: Protect Cornwall's Heritage
Ambition: Develop innovative ways to strengthen and enhance Cornwall’s tangible, intangible and natural heritage
Action | Timescale | Lead | Additional support & involvement | Sub Committee | Budget and source of funding | Performance indicator(s) | Progress | Monitoring
2.1 Saving Sites - “Save” historic sites deemed to be “at risk”.
Define and agree a sites acquisiton strategy | Quarter 2 | CW | Sites Officer, Proj Mgr, Property Committee | Property | No additional cost | Presentation of a draft Sites Acquisition Strategy to Council of Management
Identify opportunities for "new" sites - create a pipeline | Quarter 3 | Sites Manager | CW, Proj Mgr, Sites Officer, Property Committee |  | No additional cost | Formulation of a researched pipeline "hit" list
Create a robust sites management strategy for each site | Quarter 4 | Sites Manager | CW, Proj Mgr, Sites Officer, Lead Ranger |  | Dependent on requirements - could involve funding for additional surveys etc | Sites management strategy in place covering the requirements of each site
Consider the creation of geographical ranger teams | Year 2
Build the volunteer base | Year 3 |  |  |  |  | Establishment of local groups at each site
Environmental | Year 3 |  |  |  |  | Embedded within the education and outreach programmes Young Rangers group has expanded to ?? regular members
Develop the sites to enable them to be removed from the HAR by reviewing interpretation, rest places etc | Year 2 |  |  |  |  | Removal of "new" sites from the HAR within ??? of acquisition
2.2 Protecting Intangible Heritage
Research the traditions and festivals surrounding our sites with a view to designing new annual events | Year 1 | Engagement Manager | Events Officer, Proj Mgr, Education Mgr | Education | No additional cost | Research will be undertaken
Seek funding for an Outreach/ Heritage Skills Manager | Quarter 4 | Engagement Manager | SLT, BDM, Fundraiser | Finance | External funding to be sought | Funding in place
Focus on the red list of endangered crafts e.g. Cornish hedging to create a programme of skills training | Years 2 & 3
2.3 Cornish Distinctiveness -Reinforce Cornish national distinctiveness
Consider how CHT can use more “incidental” Cornish language throughout its publications, signage etc | Quarter 4 | Operations Manager | Engagement Manager & Marketing Officer | Education | No additional cost | Formulation of a strategy
Audit the website and publications to ensure consistency and prominience of the language e.g. site names | Year 2 | Operations Manager | Marketing Officer |  | No additional cost | Audit complete
2.4 Heritge Careers - Expand access to heritage careers through bursaries, apprenticeships and work placements
investigate training opportunities already being offered in Cornwall – identify gaps | Years 2 & 3
Research opportunities for collaboration e.g. CREST
Explore whether there is a way to access funding to offer vocational training courses etc
Pillar: Increase Community Engagement
Ambition: Grow our annual engagement five-fold to 50,000 of all ages across the length and breadth of Cornwall.
Action | Timescale | Lead | Additional support & involvement | Sub Committee | Budget and source of funding | Performance indicator(s) | Progress | Monitoring
3.1 Equitable Access - Provide equitable accessibility to sites through education and outreach activities.
Seek funding for accessibility audits | Quarter 2 | Engagement Mgr | Fundraiser | Education | External funding to be sought | Funding in place and audits commissioned
Consider innovative approaches to providing access to the sites remotely | Quarter 4 | Engagement Mgr | Marketing Officer, Sites Manager, Proj Mgr |  | No additional cost | Strategy to be in place
Assist travel through the school transport grants scheme | Year 1 | Engagement Mgr | Education Manager, Marketing Officer, Fundraiser, Fundraising Officer |  | No additional cost | Support at least 3,500 students per year
Explore options for creating an outdoor classroom
3.2 Supporting Schools and Young People
Explore ways to reach more schools and identify the barriers and reasons "why not" | Quarter 4 | Operations Mgr | Education Mgr, Engagement Mgr | Education | No additional cost | Education & Outreach Strategy produced
Assist travel through the school transport grants scheme - identify priorities for scheme | Ongoing | Education Mgr | Operations Mgr |  | No additional cost, although additional funding to be sought to subsidise the scheme | Proposal presented to Education Committee
Seek funding for an additional education role to enable expansion of offering | Quarter 4 | Operations Mgr | Fundraiser, Income Generation Manager, SLT | Finance | External funding to be sought | Funding in place
Increase our offer to students in alternative provision and those not in education, employment or training (NEET) | Year 2 | Operations Mgr | Education Mgr |  | External funding to be sought | Plan to be in place, to include a funding strategy
Consider creating and offering placements |  | Operations Mgr | Education Mgr |  | No additional cost | Proposal in place
Consider accreditations – Learning Outside the Classroom, Forest School and Sandford Award |  | Operations Mgr | Education Mgr, Engagement Mgr |  | No additional cost | Plan in place
3.3 Volunteering Programme
Seek funding for a Volunteering Officer role | Quarter 4 | Operations Mgr | Fundraiser, Income Generation Manager | Finance | External funding to be sought | Funding to be in place to enable recruitment in Year 2
Diversify our volunteers by broadening the opportunities offered | Year 2
3.4 Well-being - Promoting the use of our sites for the benefit of people’s well-being.
Strengthen links to social prescribing groups | Quarter 4 | Engagement Mgr | Education Mgr | Education | No additional cost | Consultation to have been undertaken
Expand capacity to deliver more social prescribing groups - seek funding for an additional resource | Year 2 | Engagement Mgr | Fundraiser, BDM
Develop a Dementia Friendly Memory Box Programme | Year 2 | Engagement Mgr | Education Mgr
3.5 Promote Cornwall’s Heritage
Review the existing events offer and look at what is offered by other organisations - identify gaps and opportunities | Quarter 2 | Engagement Mgr | Events Officer, Income Generation Manager, SLT | Education | No additional cost | Review to have been completed
Identify opportunities for new events and improving the existing schedule | Quarter 3 | Engagement Mgr | Events Officer, Fundraiser, Income Generation Manager, Finance Mgr |  | No additional cost but funding to be sought to support the cost of new initiatives | Proposals for new events and activities to be in place, along with a budget
Erect 6 Pobel a Gernow plaques in the next three years | Quarter 4 | Operations Mgr | CW |  | Revenue budget - funding to be sought in addition | 1 Plaque erected in Year 1
3.6 Membership Programme
Increase the number of recruiter events | Year 1 | Engagement Mgr | Income Generation Manager | Finance | Revenue budget | Increase from 24 to 28
Promote the use of direct debit for renewals | Year 1 | Engagement Mgr | Marketing Officer, Income Generation Manager |  | Revenue budget | Increase to 20% of renewals from 13%
Enrich the membership offering to appeal to a wider audience | Quarter 4 | Engagement Mgr | Income Generation Manager |  | Revenue budget | Maintain 80% of memberships in TR and PL postcodes
Increase the number of life members | Quarter 4 | Engagement Mgr | Income Generation Manager, Marketing Officer |  | Revenue budget | 10 Additional Life Members signed-up in Year 1
Investigate ways to reduce potential risk from the EH offer being removed by diversifying our offering | Quarter 4 | Engagement Mgr | Income Generation Manager |  | Revenue budget | Strategy to be in place
Increase donations attributed to membership subscriptions | Quarter 4 | Engagement Mgr | Income Generation Manager, Marketing Officer, Fundraiser |  | Revenue budget | Increase in associated donations to equivalent of 2% of membership income
Pillar: Collaborate
Ambition: A growing and diverse network of collaborative partnerships within and beyond the heritage sector
Action | Timescale | Lead | Additional support & involvement | Sub Committee | Budget and source of funding | Performance indicator(s) | Progress | Monitoring
4.1 Supporting Landowners
Identify ways to assist with sites not owned by CHT e.g. Practical Tasks Group in West Penwith | Quarter 4 | Sites Mgr | Proj Mgr | Property | External funding to be sought | Proposal produced to enable funding to be sought
Consider expanding the programme by seeking funding and potential collaborations | Quarter 4 | Sites Mgr | Income Generation Manager, Fundraiser, Proj Mgr, Sites Mgr |  | External funding to be sought | Funding to be in progress
Seek funding for the continuation of Richie's role | Year 1 | CW | Income Generation Manager, Fundraiser, Proj Mgr, Sites Mgr |  | External funding to be sought | Funding agreed
Look at whether there are opportunities for management agreements elsewhere? | Year 2
4.2 Community Fundraising - Seek ways to raise money for the charity through community links
Establish a community fundraising scheme | Quarter 4 | Income Generation Manager | Sites Mgr, Fundraiser, SLT | Finance | Revenue budget | Strategy to be produced
Identify funding options for a Community Fundraiser | Quarter 4 | Income Generation Manager | Fundraiser, SLT |  | Funding options to be identified | Options to be presented
Maximise opportunities at sites for fundraising and PR | Quarter 4 | Income Generation Manager | Sites Mgr, Fundraiser, SLT |  | Revenue budget | Draft strategy to be produced
Income of £1,500 to be received from community fundraising | Year 1 | Income Generation Manager | Fundraiser, Fundraising Officer, Marketing Officer |  | Revenue budget | Income of £1,500 received
4.3 Forging Links
Increase collaboration with needs-led charities, i.e. Carefree | Quarter 4 | Engagement Mgr | Operations Mgr, Education Mgr | Education | External funding to be sought | Plan to be in place
Work with partner organisations to identify potential projects | Quarter 4 | CW | Income Generation Manager, SLT |  | No additional cost but funding to be sought to support the cost of new initiatives | Plan to be in place
Supporting community groups with talks and visits to sites | Year 2 | Engagement Mgr | Education Mgr
4.4 Promote and Build the Heritage Friends Scheme
Expand the number of business supporters to achieve a 15% increase in income | Quarter 4 | Income Generation Manager | Fundraiser, Fundraising Officer, SLT, Finance Mgr | Finance | Revenue budget | At least £31,050 received
Pillar: Nancealverne
Action | Timescale | Lead | Additional support & involvement | Sub Committee | Budget and source of funding | Performance indicator(s) | Progress | Monitoring
5.1 Create and implement a fully costed Business Plan for the various activities at the property with the view to breaking even by 2029 and generating a surplus by 2031
Holiday accommodation to be up and running | Quarter 2 | Operations Mgr | CW, Design Officer | Finance | Revenue budget | At least two units to be available to let this summer
Additional governance and policies to be in place - including risk assessments etc | Quarter 3 | Operations Mgr | CW | Finance | Revenue budget | Risk assessments etc required for holiday lets to be in place by Q2, remainder by Q3
Fundraising strategy to be formulated | Quarter 4 | CW | Income Generation Manager | Finance | No additional cost | Strategy to be in place and ready to implement
Investigate "corporate" income generation opportunities | Quarter 4 | CW | Income Generation Manager | Finance | Revenue budget for wedding consultant fees | Strategy to be in place and licences etc secured
Staffing and management plan to be created and costed | Year 2 | CW | Income Generation Manager and Finance Mgr | Finance
5.2 Formulate a strategy for sharing the collections, stories, house and grounds with the public. House to be open to the public in 2027.
Policies and procedures to be designed and in place | Quarter 4 | Engagement Mgr | Operations Mgr | Education | No additional cost | All policies, risk assessments etc to be in place
Visitor experience strategy to be created for grounds and house | Quarter 4 | Engagement Mgr | Project Manager, Design Officer | Education | No additional cost | Strategy to be in place and costed for implementation
Interpretation plan to be formulated | Year 2 | Engagement Mgr | Project Manager, Design Officer | Education
Volunteering strategy to be formulated | Year 2 | Operations Mgr | Sites Manager | Education & Property?
5.3 Assess the collections within the house and ensure that they are well conserved, maintained and interpreted to enable enjoyment by future generations
Oral history project to be instigated - starting with the family | Quarter 3 | Engagement Mgr | Education Mgr | Education | Revenue budget | Project to be under-way and plans in place for wider community engagement
Create a Collections Strategy for the care, maintenance and interpretation of the collection | Quarter 4 | Engagement Mgr |  | ? | Revenue budget | Strategy to be in place and implemented
5.4 Introduce an annual programme of maintenance to ensure that the property and grounds are safe and well cared-for
Maintenance plan for house and grounds to be formulated starting with the outcome of the structural survey | Quarter 4 | CW | Project Mgr, Sites Mgr | Property | No additional cost | Plan to be in place
5.5 Identify future projects and programmes and plan them into the ongoing strategy
Consider the historic features in the grounds and buildings and design a plan for further investigation | Year 2

## Gantt
Cornwall Heritage Trust
Business Plan - Gantt
Year 1 - 2026-2027
|  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
|  |  | Q1 Apr - Jun 2026 | Q2 Jul - Aug 2026 | Q3 Sept - Dec 2026 | Q4 Jan - Mar 2027 | Q1 Apr - Jun 2027 | Q2 Jul - Aug 2027 | Q3 Sept - Dec 2027 | Q4 Jan - Mar 2028 | Q1 Apr - Jun 2028 | Q2 Jul - Aug 2028 | Q3 Sept - Dec 2028 | Q4 Jan - Mar 2029
Resilient Organisation | 1.1 Build and Diversify Revenue streams to achieve sustainable annual income of £2m, of which £1m is unrestricted, by 2031. Unrestricted funds to at least break even
| Create a role description for an Income Generation Manager role | Quarter 1 | Completed Mar 26
| Advertise and recruit Income Generation Manager role | Quarter 2 | Advertised Mar 26
| Revisit the Fundraising Strategy | Quarter 2
| Research options for income generation | Quarter 3
| Consider solutions | Quarter 4
| Formulate an Income Generation Strategy | Quarter 4
| Create a Business Plan for implementation | Quarter 4
1.2 Strengthen governance and support functions to underpin the organisation’s growth
| Creation and implementation of a robust, challenging but achievable strategic plan with associated detailed Business Plan for Year 1 (2026/27) | Pre Year 1
| Carry out skills audit for trustees alongside creating a succession plan | Year 1
| Ensure policies and procedures are in place for a growing organisation | Year 1
| Review sub committee terms of reference | Year 2
1.3 Review people team in line with expanding activity to enable delivery of the ambitions of the charity
| Identify the level of investment required to future-proof the sites team with the resources needed to manage the sites well | Year 1
| Recruit as required to fulfil the requirements of the Strategic Plan | Year 1
| Identify new solutions for technology etc | Year 2
| Explore options for a permanent headquarters for CHT | Year 2
| Seek funding to help with the cost | Year 1 & 2
1.4 Creation of a resource plan to ensure that the teams are fully equipped to meet the needs of increased activity.
| Create a resources strategy for the rolling replacement and renewal of essential kit throughout the organisation e.g. laptops | Year 1
| Capital Works Plan to be formulated for all sites | Year 1
1.5 Patron - Seek high-profile patrons to help spread the word about Cornwall’s heritage and the charity
| Identify potential Patrons | Years 2 & 3
Plan approaches
Protect Cornwall's Heritage | 2.1 Saving Sites - “Save” historic sites deemed to be “at risk”.
| Define and agree a sites acquisiton strategy | Quarter 2
| Identify opportunities for "new" sites - create a pipeline | Quarter 3
| Create a robust sites management strategy for each site | Quarter 4
| Consider the creation of geographical ranger teams | Year 2
| Build the volunteer base | Year 3
| Environmental | Year 3
| Develop the sites to enable them to be removed from the HAR by reviewing interpretation, rest places etc | Year 2
2.2 Protecting Intangible Heritage
| Research the traditions and festivals surrounding our sites with a view to designing new annual events | Year 1
| Seek funding for an Outreach/ Heritage Skills Manager | Quarter 4
| Focus on the red list of endangered crafts e.g. Cornish hedging to create a programme of skills training | Years 2 & 3
2.3 Cornish Distinctiveness -Reinforce Cornish national distinctiveness
| Consider how CHT can use more “incidental” Cornish language throughout its publications, signage etc | Quarter 4
| Audit the website and publications to ensure consistency and prominience of the language e.g. site names | Year 2
2.4 Heritge Careers - Expand access to heritage careers through bursaries, apprenticeships and work placements
| investigate training opportunities already being offered in Cornwall – identify gaps | Years 2 & 3
Research opportunities for collaboration e.g. CREST
Explore whether there is a way to access funding to offer vocational training courses etc
Increase Community Engagement | 3.1 Equitable Access - Provide equitable accessibility to sites through education and outreach activities.
| Seek funding for accessibility audits | Quarter 2
| Consider innovative approaches to providing access to the sites remotely | Quarter 4
| Assist travel through the school transport grants scheme | Year 1
Explore options for creating an outdoor classroom
3.2 Supporting Schools and Young People
| Explore ways to reach more schools and identify the barriers and reasons "why not" | Quarter 4
| Assist travel through the school transport grants scheme - identify priorities for scheme | Ongoing
| Seek funding for an additional education role to enable expansion of offering | Quarter 4
| Increase our offer to students in alternative provision and those not in education, employment or training (NEET) | Year 2
Consider creating and offering placements
Consider accreditations – Learning Outside the Classroom, Forest School and Sandford Award
3.3 Volunteering Programme
| Seek funding for a Volunteering Officer role | Quarter 4
| Diversify our volunteers by broadening the opportunities offered | Year 2
3.4 Well-being - Promoting the use of our sites for the benefit of people’s well-being.
| Strengthen links to social prescribing groups | Quarter 4
| Expand capacity to deliver more social prescribing groups - seek funding for an additional resource | Year 2
| Develop a Dementia Friendly Memory Box Programme | Year 2
3.5 Promote Cornwall’s Heritage
| Review the existing events offer and look at what is offered by other organisations - identify gaps and opportunities | Quarter 2
| Identify opportunities for new events and improving the existing schedule | Quarter 3
| Erect 6 Pobel a Gernow plaques in the next three years | Quarter 4
3.6 Membership Programme
| Increase the number of recruiter events | Year 1
| Promote the use of direct debit for renewals | Year 1
| Enrich the membership offering to appeal to a wider audience | Quarter 4
| Increase the number of life members | Quarter 4
| Investigate ways to reduce potential risk from the EH offer being removed by diversifying our offering | Quarter 4
| Increase donations attributed to membership subscriptions | Quarter 4
Collaborate | 4.1 Supporting Landowners
| Identify ways to assist with sites not owned by CHT e.g. Practical Tasks Group in West Penwith | Quarter 4
| Consider expanding the programme by seeking funding and potential collaborations | Quarter 4
| Seek funding for the continuation of Richie's role | Year 1
| Look at whether there are opportunities for management agreements elsewhere? | Year 2
4.2 Community Fundraising - Seek ways to raise money for the charity through community links
| Establish a community fundraising scheme | Quarter 4
| Identify funding options for a Community Fundraiser | Quarter 4
| Maximise opportunities at sites for fundraising and PR | Quarter 4
| Income of £1,500 to be received from community fundraising | Year 1
4.3 Forging Links
| Increase collaboration with needs-led charities, i.e. Carefree | Quarter 4
| Work with partner organisations to identify potential projects | Quarter 4
| Supporting community groups with talks and visits to sites | Year 2
4.4 Promote and Build the Heritage Friends Scheme
| Expand the number of business supporters to achieve a 15% increase in income | Quarter 4
Nancealverne | 5.1 Create and implement a fully costed Business Plan for the various activities at the property with the view to breaking even by 2029 and generating a surplus by 2031
| Holiday accommodation to be up and running | Quarter 2
| Governance and policies to be in place - including risk assessments etc | Quarter 3
| Fundraising strategy to be formulated | Quarter 4
| Investigate "corporate" income generation opportunities | Quarter 4
| Staffing and management plan to be created and costed | Year 2
5.2 Formulate a strategy for sharing the collections, stories, house and grounds with the public. House to be open to the public in 2027.
| Policies and procedures to be designed and in place | Quarter 4
| Visitor experience strategy to be created for grounds and house | Quarter 4
| Interpretation plan to be formulated | Year 2
| Volunteering strategy to be formulated | Year 2
5.3 Assess the collections within the house and ensure that they are well conserved, maintained and interpreted to enable enjoyment by future generations
| Oral history project to be instigated - starting with the family | Quarter 3
| Create a Collections Strategy for the care, maintenance and interpretation of the collection | Quarter 4
5.4 Introduce an annual programme of maintenance to ensure that the property and grounds are safe and well cared-for
| Maintenance plan for house and grounds to be formulated starting with the outcome of the structural survey | Quarter 4
5.5 Identify future projects and programmes and plan them into the ongoing strategy
| Consider the historic features in the grounds and buildings and design a plan for further investigation | Year 2
Planned timescale
Completed/ on track
Not yet complete/ nearly due
Overdue/ delayed

## Risk Register
Cornwall Heritage Trust
Business Plan - Risk Register
Year 1 - 2026-2027
Objective | Action | Description of Potential Risk | Lead | Likelihood | Impact | Score | Mitigation | Revised Likelihood | Revised Impact | Revised Score | Status | Last Updated
1.1 | Advertise and recruit Business Development Manager role | Recruit as required to fulfil the requirements of the Strategic Plan | CW | Possible (3) | Major (4) | 12 | Role has been widely advertised across a variety of platforms. There is time to re-advertise if necessary. We have already received several applications | Unlikely (2) | Moderate (3) | 6 | Ongoing - advert is live, closing date 30/3/26 | 2026-03-23 | Scores | Likelihood | Impact | Cumulative
1.3 | Recruit as required to fulfil the requirements of the Strategic Plan | Recruit as required to fulfil the requirements of the Strategic Plan | CW | Possible (3) | Moderate (3) | 9 | Role not yet been advertised but will be shared widely across various platforms and our networks | Unlikely (2) | Moderate (3) | 6 | Not yet advertised | 2026-03-23 | 5 | Certain | Severe | 25
2.1 | Create a robust sites management strategy for each site | Sites management strategy not in place by the end of the year | Sites Manager | Possible (3) | Major (4) | 12 | Advertise for Sites Manager when budget agreed - this piece of work to be a priority for them to oversee | Unlikely (2) | Moderate (3) | 6 | Sites Manager role not yet advertised | 2026-03-23 | 4 | Almost Certain | Major | 16
3.2 | Seek funding for an additional education role to enable expansion of offering | Funding not sourced and role not yet possible - will have an impact on the expansion of the education programme | Operations Manager | Possible (3) | Major (4) | 12 | Operations Manager will take on responsibility for education programme alongside Caroline. Income Generation Manager will help to source funding for the new role | Possible (3) | Moderate (3) | 9 | Recruitment in progress for the Income Generation Manager role | 2026-03-23 | 3 | Possible | Moderate | 9
3.3 | Seek funding for a Volunteering Officer role | Funding not sourced and role not yet possible - will have an impact on the expansion of the education programme | Operations Manager | Possible (3) | Major (4) | 12 | This will free-up Sarah's time to take on the education programme and so there is a potential knock-on effect. Income Generation Manager will help to source funding for the new role | Possible (3) | Moderate (3) | 9 | Recruitment in progress for the Income Generation Manager role | 2026-03-23 | 2 | Unlikely | Minor | 4
3.5 | Erect 6 Pobel a Gernow plaques in the next three years | Time restraints mean that the plaques are not erected | Operations Manager | Possible (3) | Major (4) | 12 | Carolyn will take on responsibility for the operations of this scheme while she is in post | Unlikely (2) | Minor (2) | 4 | Carolyn yet to be told! | 2026-03-23 | 1 | Negligible | Negligible | 1
3.6 | Increase the number of recruiter events | Number of recruiter events not increased leading to an impact on income from memberships | Engagement Manager | Possible (3) | Major (4) | 12 | Recruiter events already being booked-in and diary looks full - more attendance at events planned than last year | Possible (3) | Moderate (3) | 9 | Katie is booking-in events | 2026-03-23
4.1 | Seek funding for the continuation of Richie's role | Without additional funding the Practical Tasks Group will have to finish | CW | Possible (3) | Severe (5) | 15 | Will include in grant applications and projects, Income Generation Manager will support | Possible (3) | Moderate (3) | 9 | Funding in place until December 2026 | 2026-03-23
4.2 | Establish a community fundraising scheme | Scheme is not established and projected income not realised | Income Generation Manager | Possible (3) | Major (4) | 12 | Small target for this year means that we can start small and expand. Income Generation Manager role is being advertised | Unlikely (2) | Moderate (3) | 6 | Recruitment in progress for the Income Generation Manager role | 2026-03-23
4.4 | Expand the number of business supporters to achieve a 15% increase in income | Projected growth not achieved and has an impact on income figures for the year | Income Generation Manager | Possible (3) | Major (4) | 12 | Income Generation Manager will lead on this with support from Antonia | Possible (3) | Moderate (3) | 9 | Recruitment in progress for the Income Generation Manager role | 2026-03-23
5.1 | Holiday accommodation to be up and running | Unable to open lets and income generation is affected | Operations Manager | Possible (3) | Major (4) | 12 | Sarah is consulting agencies and taking advice from the donors; an action plan is in place | Unlikely (2) | Moderate (3) | 6 | Work is underway ahead of the transfer | 2026-03-23